## SRTP T&F Readiness check-list
SRTP Homologation - Technical & Functional Testing checklist
# | Category | Conditions | Version | Purpose | Who (Owner) | Status | Info-Comment-Action | When ready? (Date)
1 | Documentation | Rulebook "EPC014-20 v3.2 SEPA RTP Scheme Rulebook" implemented? | V3.2 | Ensure compliance with the applicable SRTP specifications | Applicant/TSP | CHECK
2 | Documentation | Rulebook Guidance according "EPC216-20 v3.1 Clarification Paper SRTP Rulebook" consulted? | V3.1 | Provide guidance and recommendations on SRTP rulebook implementation. | Applicant/TSP | CHECK
3 | Documentation | Implementation guidelines between the Payee and his RTP Service Provider : "EPC258-22 Payee-Payee's RTP SP SRTP IG V3.0" are implemented? | V3.0 | Ensure compliance with the applicable SRTP specifications | Applicant/TSP | CHECK | Only if relevant for the applicant/TSP.
4 | Documentation | Implementation Guidelines between RTP Service Providers : "EPC259-22 Inter-RTP SP SRTP IG V3.0" implemented? | V3.0 | Ensure compliance with the applicable SRTP specifications | Applicant/TSP | CHECK
5 | Documentation | Implementation Guidelines between the Payer and his RTP Service Provider : "EPC260-22 Payer-Payer's RTP SP SRTP IG V3.0" implemented? | V3.0 | Ensure compliance with the applicable SRTP specifications | Applicant/TSP | CHECK | Only if relevant for the applicant/TSP.
6 | Documentation | Application Programming Interface according "EPC SRTP related API Specifications - Preliminary Information" (EPC137-22) implemented? | V3.1 | Ensure compliance with API specifications | Applicant/TSP | CHECK
7 | Documentation | Application Programming Interface according the YAML file "EPC SRTP Scheme Rulebook v3.1 related API Specifications" (EPC133-22) implemented? | V3.1 | Ensure compliance with API specifications | Applicant/TSP | CHECK
8 | Documentation | Application Programming Interface Security Framework according "EPC API Security Framework" (EPC164-22) implemented? | V1.0 | Ensure compliance with the security-related requirements using API's | Applicant/TSP | CHECK
9 | Documentation | The Testing Guide "Technical and Functional Testing Homologation Guide" read and understood? | V2.0 | A clear understanding of the testing process | Applicant/TSP | CHECK |  |  | kl
10 | Documentation | The Test Plan according "SEPA_RTP_Test_Plan-GALITT" read and understood? | V5.0 | Be prepared for all required tests and their associated amounts | Applicant/TSP | CHECK
11 | Testing | The testing environment for homologation testing is available? | N.A. |  | Applicant/TSP | CHECK
12 | Testing | The SRTP system has been successfully tested according the above mentioned specification documents? | N.A. | Ensuring a successful homologation technical and functional testing | Applicant/TSP | CHECK
13 | Testing | The Applicant/TSP has provided the Homologation Body with an example of each of the following message type filled with its own test data : DS-02, DS-04b, DS-08, DS-11, DS-15(RTP), DS-16(RfC) (see "Message example" tab) | N.A. | Ensuring a successful homologation technical and functional testing | Applicant/TSP | CHECK
14 | Connectivity | For testing purposes an URL endpoint can be used for communication with the Applicant/TSP? | N.A. | Ensuring connectivity between Applicant and HB | Applicant/TSP | CHECK
15 | Connectivity | The Applicant/TSP endpoint URL(s) and connectivity features (server host name, timeouts, different IP addresses...) are provided? | N.A. | Ensuring connectivity between Applicant and HB | Applicant/TSP | CHECK
16 | Connectivity | The Applicant/TSP has setup and tested the DNS provided by the Homologation Body? | N.A. | Ensuring connectivity between Applicant and HB | Applicant/TSP | CHECK | Target = 51.178.113.33 for https://testing-srtp.galitt.com/005/ or https://testing-srtp.galitt.com/006/
17 | Connectivity | The Applicant/TSP has setup and tested the QWAC certificate provided by the Homologation Body? | N.A. | Ensuring connectivity between Applicant and HB | Applicant/TSP | CHECK
18 | Connectivity | The Applicant/TSP provided the QWAC certificate with a profile based on the European Standard ETSI EN 319 412-4. | N.A. |  | Applicant/TSP | CHECK
19 | Connectivity | The Homologation Body has configured the applicant URL as end-point? | N.A. |  | HB | CHECK
20 | Connectivity | The Applicant/TSP has configured the homologation Body URL as end-point? | N.A. | Ensuring connectivity between Applicant and HB | Applicant/TSP | CHECK | https://testing-srtp.galitt.com/00X/sepa-request-to-pay-requests
21 | Connectivity | Homologation Body allowed traffic with Applicant/TSP IP address? | N.A. | Ensuring connectivity between Applicant and HB | HB | CHECK
22 | RTP identifiers | Homologation SRTP identifiers are registered? | N.A. | To register HB identifiers as a trusted RTP SP | Applicant/TSP | CHECK | see included sheet : Homologation RTP Identifiers
23 | RTP identifiers | Applicant/TSP SRTP identifiers are provided? (Examples : Payer BIC & IBAN, …) | N.A. | To register Applicant identifiers as a trusted RTP SP | Applicant/TSP | CHECK
24 | RTP identifiers | Applicant/TSP SRTP identifiers are registered? | N.A. | To register Applicant identifiers as a trusted RTP SP | HB | CHECK
25 | Responsibilities | The applicant/TSP provides support to the testing team during the entire testing period for planned (payee part) as well as non-planned (payer part) test sessions. | N.A. |  | Applicant/TSP | CHECK
26 | Responsibilities | Applicant/TSP testing contact person(s) and contact details (email address, ...) provided? | N.A. | Ensuring efficient communication and remediation to respect the planning | Applicant/TSP | CHECK
27 | Responsibilities | Applicant/TSP overall contact responsible for homologation and contact details provided? | N.A. | Ensuring efficient communication and remediation to respect the planning | Applicant/TSP | CHECK
28 | Responsibilities | Homologation Body testing contact person(s) and contact details (email address, ...) provided? | N.A. | Ensuring efficient communication and remediation to respect the planning | HB | CHECK | Bruno Dubois - SRTPHomologation@soprasteria.com - +33 6 70 26 77 21
29 | Responsibilities | Homologation body Lead assessor responsible for homologation and contact details provided? | N.A. | Ensuring efficient communication and remediation to respect the planning | HB | CHECK | Danny Smeulders - SRTPHomologation@soprasteria.com - +32 49 58 60 64
30 | Planning | Connectivity tests are scheduled? | N.A. | Ensuring efficient execution of testing | HB + Applicant/TSP | CHECK
31 | Planning | Technical and functional tests are scheduled? | N.A. | Ensuring efficient execution of testing | HB + Applicant/TSP | CHECK
| TSP: | Technical Solution Provider
Note on F2: Applicant : candidate SRTP scheme participant TSP : Candidate Referenced Technical Solution provider HB : Homologation Body

## Message example
Example of expected format with a DS-02 message :
{"callbackUrl":"https://testing-srtp.galitt.com/005/callback","Document":{"CdtrPmtActvtnReq":{"GrpHdr":{"MsgId":"Id2024030410462895147229","CreDtTm":"2024-03-04T10:44:02.000Z","NbOfTxs":"1","InitgPty":{"Nm":"SRTPTestEPC ","Id":{"OrgId":{"AnyBIC":"AAAAZZ12"}}}},"PmtInf":[{"PmtInfId":"Id2024030410462896618800","PmtMtd":"TRF","ReqdAdvcTp":{"CdtAdvc":{"Cd":"ADND"},"DbtAdvc":{"Cd":"ADND"}},"ReqdExctnDt":{"DtTm":"2024-03-23T10:44:01.000Z"},"XpryDt":{"DtTm":"2024-03-18T10:44:01.000Z"},"Dbtr":{"Nm":"Max140Text_EPC259-22_V3.0_DS02","PstlAdr":{"Ctry":"FR","AdrLine":["01 Rue de Paris"]},"Id":{"OrgId":{"AnyBIC":"AAAAZZ12"}}},"DbtrAcct":{"Id":{"IBAN":"FI5571401220000438"},"Nm":"Nm"},"DbtrAgt":{"FinInstnId":{"BICFI":"AAAABBBB"}},"CdtTrfTx":[{"PmtId":{"InstrId":"InstrId ","EndToEndId":"EndtoEnd "},"PmtTpInf":{"SvcLvl":{"Cd":"SRTP"},"LclInstrm":{"Cd":"CTP"},"CtgyPurp":{"Cd":" "}},"PmtCond":{"AmtModAllwd":false,"EarlyPmtAllwd":true ,"GrntedPmtReqd":false},"Amt":{"InstdAmt":2024},"ChrgBr":"SLEV","CdtrAgt":{"FinInstnId":{"BICFI":"AAAAZZ11"}},"Cdtr":{"Nm":"Max140Text_EPC259-22_V3.0_DS02","PstlAdr":{"Ctry":"FR","AdrLine":["01 Rue de Paris"]},"Id":{"OrgId":{"AnyBIC":"AAAAZZ12"}}},"CdtrAcct":{"Id":{"IBAN":"FR7630003035710005023922834"}},"InstrForCdtrAgt":[{"InstrInf":"ATS007 Positive functional confirmation requested"}],"Purp":{"Cd":"ADCS"},"RltdRmtInf":{"RmtId":"RmtId","RmtLctnDtls":[{"Mtd":"URID","ElctrncAdr":"ElctrncAdr"}]},"RmtInf":{"Ustrd":["approval timeout"]}}]}]}},"resourceId":"6133-3180-9504-9008"}

## Homologation RTP Identifiers
Attribute | Value | Value type
AT-C001 IBAN of the Payee | FR7630003035710005023922834 | IBAN
AT-E001 Name of the Payee | SRTPTestEPCXX | Text
AT-E005 Payee’s identification code | BICPYE01 | ID
AT-N002 Identifier of the Payee’s RTP Service Provider | PSPYEE11234 | BIC
AT-N001 Identifier of the Payer’s RTP Service Provider | PSPYER11235 | BIC
AT-S011 Additional unique reference provided by the Payee’s RTP Service Provider | InstrId | Text
AT-T001 Identification code of the Scheme | SEPA | Text
AT-P009 Identifier of the Payer | BICPYR02 | BIC